
EN

	[image: image1.wmf]
	EUROPEAN COMMISSION


Brussels, 21.10.2010

COM(2010) 589 final
 
REPORT FROM THE COMMISSION

ANNUAL REPORT ON THE COHESION FUND (2009)



SEC(2010) 1231 final

TABLE OF CONTENTS
1.
Financial execution of the 2000-2006 period in 2009 and closure of projects
3
2.
Economic environment and conditionality
7
3.
Audits and financial corrections
8
4.
Irregularities notified by the Member States
11
5.
Evaluation
12
6.
Information and publicity
13
Regulation (EC) No 1084/2006 establishing a Cohesion Fund and repealing Regulation (EC) No 1164/94 does not require the presentation of an annual report on the Cohesion Fund.
Therefore this report is presented in conformity with Article 14(1) of Regulation (EC) No 1164/1994 and thus covers the implementation during 2009 of Cohesion Fund projects adopted under the 2000-2006 period as well as ex-ISPA projects in the Member States concerned, including Bulgaria and Romania.

As a consequence, this report covers Cohesion Fund operations in the thirteen beneficiary Member States as of end-2006, i.e. Greece, Spain, Portugal, Cyprus, Czech Republic, Estonia, Hungary, Latvia, Lithuania, Malta, Poland, Slovakia and Slovenia, as well as ex-ISPA projects adopted in the 2000-2006 period in Bulgaria and Romania. It must be recalled that, as a result of economic growth, Ireland has not been eligible since 1 January 2004, nevertheless, on-going Cohesion Fund projects are still to be closed.
Details on the implementation in 2009 of projects adopted under the 2000-2006 period for each Member State are presented in the Annex to this report.
1.
Financial execution of the 2000-2006 period in 2009 and closure of projects

Payments made in 2009 for projects adopted under the 2000-2006 period

Given that all commitments for the Cohesion Fund projects financed under the 2000‑2006 programming period have been executed by 31 December 2006, the financial resources available for the Cohesion Fund in 2009 were limited only to payment appropriations. 

The 2009 initial budget for the 2000-2006 Cohesion Fund projects amounted to EUR 3,892 million. However, the final budget was reduced to EUR 2,777 million. The cut is justified by significantly better execution in 2008, where payments exceeded the voted budget by nearly 30 %. In order to cover the gap between the available resources and the demand for payments in 2008, transfers have been made from the budget line related to the 2007-2013 Cohesion Fund programmes. This was caused by a lower start-up of the 2007-2013 period and thus in 2008 the Member States opted to balance the delay by focusing on the implementation of the 2000-2006 projects. 
In 2009 the trend was reversed and the outstanding 2000-2006 payment appropriations have been transferred to the 2007-2013 Cohesion Fund and ERDF programmes, which allowed for 100 % execution of payments credits for the Cohesion Fund programmes and projects financed under both programming periods. The available appropriations of EUR 2,777 million have been fully executed by the end of 2009, resulting in nearly EUR 300 million more payments made in 2009 when compared with the 2008 execution (EUR 2,489 million). 
As far as the ex-ISPA budget lines are concerned, the available appropriations have been executed at 100 %. 

At the end of 2009, the average absorption rate (payments vs. commitments) of all current beneficiary countries for both the Cohesion Fund and former ISPA projects was 75.8 %. The low absorption for Bulgaria at the end of 2008 (39.8 %) significantly improved in the course of 2009, resulting in a rate of 56.5 %. The other Member States range between 65.8 % (Poland and Romania) and 92.8 % (Ireland).

Table 1: Implementation of the Cohesion Fund and ex-ISPA payments in 2009 (Euro)
	Payment Appropriations
	Initial
	Movements
	Final Resources
	Outturn
	Carryovers 2010

	Cohesion Fund
	3.892.453.278
	-1.115.315.452 
	2.777.137.826
	2.777.137.825
	-

	Ex-ISPA
	400.000.000
	+128.969.059
	528.969.059
	528.969.059
	-

	TOTAL
	4.292.453.278
	-986.346.395
	3.306.106.885
	3.306.106.885
	


Table 2 shows the level of 2009 payments for each Member State. The payments done in the framework of the ex-ISPA contribution are included, as they have all been turned into Cohesion Fund projects at the date of the accession. Main beneficiary countries are Spain in the EU-4 group, Poland in the EU-10 group and Romania in the EU-2 group. 

Table 2: Payments made in 2009 to Cohesion Fund and ex-ISPA projects per Member State (including technical assistance)
	Member State 
	Environment
	Transport
	Technical Assistance
	TOTAL

	
	Amount
	%

(as compared to the CF 2009 outturn by MS)
	Amount
	%
(as compared to the CF 2009 outturn by MS)
	Amount
	Amount
	%

(as compared to the global CF amount)

	Greece 
	87.787.992
	32,8%
	179.354.927
	67,0%
	483.890
	267.626.809
	8,1%

	Portugal 
	217.958.948
	69,4%
	95.310.572
	30,4%
	662.867
	313.932.387
	9,5%

	Ireland 
	10.700.000
	46,7%
	12.231.279
	53,3%
	- 
	22.931.279
	0,7%

	Spain 
	438.942.360
	61,6%
	273.080.132
	38,4%
	- 
	712.022.492
	21,5%

	EU 4
	755.389.300
	57,4%
	559.976.910
	42,5%
	1.146.757
	1.316.512.967
	39,8%

	Cyprus 
	8.236.548
	100,0%
	- 
	 -
	- 
	8.236.548
	0,2%

	Czech Republic 
	110.536.127
	61,8%
	68.256.254
	38,2%
	- 
	178.792.381
	5,4%

	Estonia 
	26.598.027
	63,9%
	11.887.556
	28,6%
	3.131.117
	41.616.700
	1,3%

	Hungary 
	101.174.649
	40,8%
	145.002.371
	58,5%
	1.843.895
	248.020.915
	7,5%

	Latvia 
	23.221.184
	55,6%
	18.360.386
	43,9%
	205.401
	41.786.971
	1,3%

	Lithuania 
	54.895.917
	54,1%
	43.992.426
	43,4%
	2.548.928
	101.437.271
	3,1%

	Malta 
	- 
	- 
	- 
	- 
	2.909
	2.909
	0,0%

	Poland 
	473.658.296
	56,6%
	351.643.624
	42,0%
	11.512.473
	836.814.393
	25,3%

	Slovakia 
	46.574.012
	99,5%
	- 
	- 
	244.253
	46.818.265
	1,4%

	Slovenia 
	20.483.408
	51,4%
	19.354.671
	48,6%
	- 
	39.838.079
	1,2%

	EU 10
	865.378.168
	56,1%
	658.497.288
	42,7%
	19.488.976
	1.543.364.432
	46,7%

	Bulgaria 
	67.755.746
	46,6%
	69.324.323
	47,7%
	8.384.684
	145.464.754
	4,4%

	Romania 
	198.052.988
	65,8%
	95.213.178
	31,7%
	7.498.566
	300.764.732
	9,1%

	EU 2
	265.808.734
	59,6%
	164.537.501
	36,9%
	15.883.250
	446.229.486
	13,5%

	TOTAL
	1.886.576.202
	57,1%
	1.383.011.699
	41,8%
	36.518.983
	3.306.106.885
	100,0%


Outstanding commitments from the 2000-2006 period
At the end of 2009, the outstanding commitments ("reste à liquider", RAL) corresponding to the 2000-2006 period amounted to EUR 8.4 billion. 

Table 3: Cohesion Fund and ex-ISPA accepted amounts in 2000-2006 (including RAL)
	Member State
	Committed
(until 12/2009)
	Paid 
(until 12/2009)
	% Paid
	RAL 
as at 31/12/2009
	
% RAL

	Greece
	3.565.195.978
	2.715.334.857
	76,2%
	849.861.122
	23,8%

	Spain
	12.915.179.288
	10.519.496.170
	81,5%
	2.395.683.119
	18,5%

	Ireland
	625.755.407
	580.710.223
	92,8%
	45.045.184
	7,2%

	Portugal
	3.497.201.489
	2.741.059.557
	78,4%
	756.141.931
	21,6%

	TOTAL EU-4
	20.603.332.162
	16.556.600.807
	80,4%
	4.046.731.356
	19,6%

	Cyprus
	54.014.695
	40.029.810
	74,1%
	13.984.885
	25,9%

	Czech Republic
	1.226.581.086
	975.579.344
	79,5%
	251.001.742
	20,5%

	Estonia
	425.431.731
	330.768.303
	77,7%
	94.663.429
	22,3%

	Hungary
	1.481.998.333
	1.028.122.934
	69,4%
	453.875.399
	30,6%

	Latvia
	713.987.456
	541.309.058
	75,8%
	172.553.278
	24,2%

	Lithuania
	825.354.775
	661.411.795
	80,1%
	163.942.980
	19,9%

	Malta
	21.966.289
	17.532.611
	79,8%
	4.433.678
	20,2%

	Poland
	5.634.539.614
	3.708.555.930
	65,8%
	1.925.983.684
	34,2%

	Slovakia
	766.117.246
	586.031.109
	76,5%
	180.086.137
	23,5%

	Slovenia
	254.197.825
	202.417.662
	79,6%
	51.780.164
	20,4%

	TOTAL EU-10
	11.404.063.930
	8.091.758.556
	71,0%
	3.312.305.376
	29,0%

	Bulgaria
	876.947.183
	495.486.300
	56,5%
	381.460.884
	43,5%

	Romania
	2.037.250.711
	1.340.892.809
	65,8%
	696.357.902
	34,2%

	TOTAL EU 2
	2.914.197.894
	1.836.379.109
	63,0%
	1.077.818.786
	37,0%

	TOTAL
	34.921.593.986
	26.484.738.472
	75,8%
	8.436.855.518
	24,2%


Closure of projects from the 2000-2006 period
At the end of 2009, the total number of closed Cohesion Fund projects for the 2000‑2006 period (including ex-ISPA projects) reached 299. The number of projects remaining for closure decreased from 976 at the end of 2008 to 893 at end of 2009. Table 4 provides information on the projects closed until the end of 2009 (per Member State). 

Table 4: Number of CF projects closed until the end of 2009 (including ex-ISPA)
	Member State
	Total number of CF projects
	Projects closed as of end 2009
	Number of open projects as of end 2009

	
	
	Number of Projects
	Total Paid in Euro
	

	Czech Republic
	58
	19
	350.331.885
	39

	Estonia
	37
	20
	106.548.425
	17

	Greece
	124
	49
	1.150.632.586
	75

	Spain
	407
	110
	2.969.559.629
	297

	Ireland
	10
	4
	357.368.796
	6

	Cyprus
	2
	0
	0
	2

	Latvia
	46
	10
	44.331.604
	36

	Lithuania
	51
	13
	159.495.999
	38

	Hungary
	47
	11
	26.071.037
	36

	Malta
	3
	0
	0
	3

	Poland
	130
	6
	68.915.348
	124

	Portugal
	109
	32
	810.129.887
	77

	Slovenia
	28
	10
	72.460.238
	18

	Slovakia
	39
	9
	60.041.606
	30

	EU 14
	1.091
	293
	6.175.887.040
	798

	Bulgaria
	38
	3
	27.044.270
	35

	Romania
	63
	3
	2.191.214
	60

	EU 2
	101
	6
	29.235.484
	95

	Total
	1.192
	299
	6.205.122.524
	893


2.
Economic environment and conditionality

Article 6 of the Council Regulation (EC) No 1164/94 which governs the Cohesion Fund for projects approved prior to the end of 2006 attaches budgetary policy conditions to the disbursements by the Fund. It provides that "no new projects or, in the event of important projects, no new project stages shall be financed by the Fund in a Member State in the event of the Council, acting by a qualified majority on a recommendation from the Commission, finding that the Member State […] has not implemented [its stability or convergence programme] in such a way as to avoid an excessive deficit".

At the end of 2009 eleven Member States eligible for support under the Cohesion Fund (Greece, Spain, Portugal, Czech Republic, Hungary, Latvia, Lithuania, Malta, Poland, Slovakia and Slovenia) were in the excessive deficit procedure (EDP), which, according to the aforementioned Regulation, may under certain conditions be associated with the suspension of transfers from the Fund. In 2009 there were three cases (Greece, Spain and Hungary) where effective action taken in compliance with the Council recommendations under Article 104(7) TEC was assessed. The Council decided that Spain and Hungary took effective action and issued new recommendations under Article 126(7) TFEU. Only in the case of Greece the Council decided under Article 126(8) TFEU that the authorities had not taken effective action in response to the Council recommendations to end the excessive deficit, but suspension of payments from the Cohesion Fund was not recommended at the time.
3.
Audits and financial corrections
In 2009, the focus of the audit services as regards the 2000-2006 period was on preparing for closure with review missions of the work of national winding-up bodies and in the practical closure of 2000-2006 period Cohesion Fund projects through analysis of winding-up declarations.
Audit work for Programming period 1994-1999 - EU 4 (Greece, Ireland, Portugal, Spain)

The Cohesion Fund closure enquiry concerning the period 1994-1999 covered 10% of Cohesion Fund projects representing 20% of the co-financed expenditure during this period. The fieldwork was finalised in 2003 and the main deficiencies found were insufficient management verifications resulting in ineligible expenditure and breaches of public procurement rules. The follow-up and financial correction procedures resulting from the closure enquiry were all concluded by the end of 2009, apart for one remaining case (in Spain) which is to be finalised in spring 2010.
Audit work for Programming period 2000-2006 - EU 16 (EU 10 + EU 4 + EU 2)

For EU-14 Member States, three audit missions (in Spain, Portugal, and Greece) for the review of winding-up bodies were carried out by the Directorate-General for Regional Policy in 2009 in order to verify the preparation of Member States for closure and to identify and mitigate related risks. In addition, six other audit missions were carried out in (Bulgaria, Czech Republic, Greece, Hungary, and two in Romania).
For the closure of 2000-2006 Cohesion Fund projects, the audit services of Directorate-General for Regional Policy examined the winding-up declarations submitted by the Member States. 

Other audit work undertaken for the Cohesion Fund included the examination of the national annual control reports under Article 12 of Regulation No. 1386/2002 and the review of national system audit reports submitted to the Commission. By the end of 2009, the majority of reports had been analysed, and replies sent to the Member States with observations and, where necessary, requesting additional information. 

Bilateral coordination meetings are held annually between the Commission and national audit authorities to exchange information on the implementation of audit work and to discuss progress on sample checks and follow-up of audit findings. The meetings covering audit work carried out in the year 2008 were held during the spring and summer of 2009. The annual bilateral coordination meetings covering audit work carried out in 2009 were held in spring and summer 2010.
Impact of controls

Cohesion Fund suspension decisions and financial corrections in 2009 

In the exercise of its supervisory role, the Directorate-General for Regional Policy established a policy in 2008 to ensure more rapid adoption of decisions for suspensions of payment and financial corrections when serious systems weaknesses are detected. The more rigorous approach continued in 2009.

The overall figure of financial corrections for Cohesion Fund in 2009 was approximately EUR 86 million, compared to approximately EUR 92.7 million in 2008 (concerning both 1994-1999 and 2000-2006 periods). This raises the total cumulative financial corrections for Cohesion Fund in the period 2000-2009 to EUR 233 million for the 2000-2006 period and to EUR 273 million for the 1994-1999 period. No suspension decisions were adopted for Cohesion Fund projects in 2009.

At the end of 2009, suspension and correction procedures were in progress for a total number of approximately 99 Cohesion Fund projects (2000-2006) covering about EUR 149 million. 

Table 5: Cohesion Fund financial corrections in 2009 by period and country (in EUR)

	Member State 
	Cohesion Fund
	TOTAL

	 
	Period 
	Period 
	 

	
	2000-2006
	1994-1999
	

	Bulgaria 
	2.413.615
	-
	2.413.615

	Cyprus 
	-
	-
	- 

	Czech Republic 
	113.008
	-
	113.008

	Estonia 
	-
	-
	-

	Greece 
	2.452.289
	-
	2.452.289

	Spain 
	21.592.738
	4.771.861
	26.364.599

	Hungary 
	40.497.367
	-
	40.497.367

	Ireland 
	-
	-
	-

	Latvia 
	-
	-
	-

	Lithuania 
	649.156
	-
	649.156

	Malta 
	-
	-
	-

	Poland 
	-
	-
	-

	Portugal 
	205.714
	4.987.861
	5.193.575

	Romania 
	8.067.402
	-
	8.067.402

	Slovenia 
	-
	-
	-

	Slovakia 
	-
	-
	-

	TOTAL
	75.991.289
	9.759.722
	85.751.011


Management and Control systems
In the Directorate General's Annual Activity Report for 2009, for the functioning of the management and control systems (2000-2006), an unqualified opinion was given for the Cohesion Fund systems in six Member States (Cyprus, Estonia, Greece, Malta, Portugal and Slovenia).

For nine Member States, the opinion was qualified with a moderate impact as a result of material deficiencies affecting key elements of the systems (Bulgaria - transport sector, Czech Republic, Hungary, Latvia, Lithuania, Poland, Romania, Slovakia and Spain).
Only one CF sector in one Member state (Bulgaria - environmental sector) was put under a reservation in the Directorate-General's Annual Activity report for 2009 primarily due to breaches of public procurement rules. In 2010 work is on-going to rectify the identified problems together with the national authorities.
4.
Irregularities notified by the Member States
In 2009, the Member States communicated to the Commission, in accordance with Regulation (EC) No 1831/94, altogether 109 notifications of irregularities involving a total affected amount of EUR 67,304,951 in respect of projects co-financed by the EU. From this amount, EUR 56,673,503 has been recovered, and the remaining amount still has to be recovered. The countries reporting the majority of cases are Portugal, Spain and Poland (27, 20, and 19 respectively). Portugal reported 39% of the involved amount. It is also worthwhile to note that Hungary with four notifications, is second in terms of amount involved. In addition, during the same period Bulgaria communicated to the Commission, in accordance with Regulation (EC) No 1828/2006
 applicable for the programming period 2007-2013, 17 notifications of irregularities involving a total affected amount of around EUR 3.6 million in respect of projects co-financed by the EU.
The number of notifications shows a significant decrease, compared to the previous year, however, the involved amount remains at the same level. The main types of irregularities reported are ineligible expenditure, and infringements of public procurement rules. These two typologies cover almost 75% of all cases reported.
Table 6: Irregularities communicated by Member States in 2009 (in EUR)

	Member State
	Number of irregularities
	Financial amounts
	Amounts awaiting recovery

	Bulgaria 
	17
	3.578.740
	3.578.740

	Cyprus 
	0
	0
	0

	Czech Republic 
	3
	1.924.920
	0

	Estonia 
	0
	0
	0

	Greece 
	14
	4.780.520
	1.684.211

	Spain 
	20
	4.351.765
	3.622.443

	Hungary 
	4
	18.449.851
	40.387

	Ireland 
	0
	0
	0

	Latvia 
	0
	0
	0

	Lithuania 
	2
	4.491.703
	0

	Malta 
	1
	39.133
	39.133

	Poland 
	19
	2.275.178
	49.542

	Portugal 
	27
	24.575.760
	1.332.009

	Romania 
	0
	0
	0

	Slovenia 
	1
	2.552.398
	0

	Slovakia 
	1
	284.983
	284.983

	TOTAL
	109
	67.304.951
	10.631.448


5.
Evaluation
The Commission and the Member States carry out appraisal and evaluation of all co‑financed projects. The projects to be financed by the Fund are adopted by the Commission in agreement with the beneficiary Member States.

The Commission carries out the ex-post evaluation of the Cohesion Fund. The previous evaluation was published in 2005 and looked at a sample of 200 projects implemented over the 1993-2002 period. A new ex-post evaluation was launched in 2009 looking at all Cohesion Fund and former ISPA projects implemented during the 2000-2006 period. In the framework of a set of 3 interlinked "work packages", the evaluation will assess the contribution of the Cohesion Fund and ISPA to the development of the EU transport system, to achieving the EU acquis in the field of environment and the effect of ISPA as a preparation for the Structural and Cohesion Funds programmes. In addition, ex post cost-benefit analyses will be carried out for a sample of transport and environment projects, identifying lessons for future programming periods.
6.
Information and publicity
As indicated in the annual report for 2007, issues concerning the Cohesion Fund are, as from 1 January 2007, dealt within the Coordination Committee of the Funds (COCOF, according to Regulation (EC) No 1083/2006).

Several issues of common interest for ERDF and Cohesion Fund were presented or discussed during the meetings of the COCOF in 2009, for example:
· Commission Regulation amending Regulation (EC) No 1828/2006 setting out rules for the implementation of Council Regulation (EC) No 1083/2006 laying down general provisions on the European Regional Development Fund, the European Social Fund and the Cohesion Fund and of Regulation (EC) No 1080/2006 of the European Parliament and of the Council on the European Regional Development Fund;
· Commission decision amending the Decision concerning the financing of the programme for the use of operational and non-operational technical assistance at the initiative of or on behalf of the European Commission under the European Regional Development Fund (ERDF) and the Cohesion Fund (CF) for 2009;

· Commission decision concerning the financing of the programme for the use of operational and administrative technical assistance at the initiative or on behalf of the European Commission under the European Regional Development Fund (ERDF) and the Cohesion Fund (CF) for 2010;

As regards the Commission measures on information and publicity, the focus in 2009 was two-fold. First, to ensure the publication of the list of beneficiaries of EU Funds managed by the Commission in partnership with Member States in line with Article 7.2 of Commission Regulation (EC) No 1828/2006. Second, the Directorate-General for Regional Policy published details of major projects, including those financed by the Cohesion Fund, both for the 2000-2006 and 2007-2013 period. The details of many of these projects are available in a searchable database on the INFOREGIO website. To date, there are over 300 projects listed in the database (which include major projects and other projects financed through the 2007-2013 programmes).
�	Includes corrections made by Member States, following agreement under the relevant procedure or as a result of implementation of action plans and formal Commission decisions. Includes corrections implemented as a result of Commission audit work but also corrections carried out in the course of implementation or closure of projects.


�	OJ L 371, 27.12.2006, p.1, as amended by Regulation (EC) No 846/2009, OJ L 250,23.09.2009





EN

 
EN

